## Sheet1
Identify the hardware team
Task ID: 7
Start Date: 20191030
Finish Date: 20191030
Responsible: Group
Identify the software team
Task ID: 8
Start Date: 20191030
Finish Date: 20191030
Responsible: Group
Brain storm
Task ID: 9
Start Date: 20191030
Finish Date: 20191101
Responsible: Group
Chassis design
Task ID: 10
Start Date: 20191101
Finish Date: 20191104
Responsible: hardware Group
Software logic design
Task ID: 20
Start Date: 20191105
Finish Date: 20191108
Responsible: software group
Sketches
Task ID: 11
Start Date: 20191104
Finish Date: 20191106
Responsible: hardware Group
Download the arduino programs
Task ID: 21
Start Date: 20191108
Finish Date: 20191108
Responsible: software group
view and edit the arduino programs
Task ID: 22
Start Date: 20191108
Finish Date: 20191112
Responsible: software group
Agree with the best design
Task ID: 15
Start Date: 20191106
Finish Date: 201911107
Responsible: hardware Group
Draft in cad
Task ID: 16
Start Date: 20191107
Finish Date: 20191110
Responsible: hardware Group
Assamble the parts in cad
Task ID: 17
Start Date: 20191110
Finish Date: 20191110
Responsible: hardware Group
Presentation Day
Task ID: 33
Start Date: 20191210
Finish Date: 20191210
Responsible: hardware Group
Test the program
Task ID: 23
Start Date: 20191112
Finish Date: 2019113
Responsible: hardware Group
Review the program
Task ID: 24
Start Date: 20191113
Finish Date: 2019118
Responsible: hardware Group
CardBoard prototype
Task ID: 18
Start Date: 20191110
Finish Date: 20191112
Responsible: hardware Group
3D print submit
Task ID: 19
Start Date: 20191110
Finish Date: 20191112
Responsible: hardware Group
caculate the cost
Task ID: 25
Start Date:
Finish Date:
Responsible:
Revision of each assignment
Task ID: 32
Start Date:
Finish Date:
Responsible: Group
Note book
Task ID: 30
Start Date:
Finish Date:
Responsible: Group
Write the introduction of each section in Design Binder
Task ID: 31
Start Date:
Finish Date:
Responsible: Group
Concept generation
Task ID: 12
Start Date: 20191101
Finish Date: 20191104
Responsible: hardware Group
Concept scoring
Task ID: 13
Start Date:
Finish Date:
Responsible:
concept screening
Task ID: 14
Start Date:
Finish Date:
Responsible:
penalties for lack of participation
Task ID: 26
Start Date:
Finish Date:
Responsible:
Creat PPT
Task ID: 27
Start Date:
Finish Date:
Responsible:
Assamble the robot
Task ID: 28
Start Date:
Finish Date:
Responsible:
Presentation practice
Task ID: 29
Start Date: 20191210
Finish Date: 20191210
Responsible: hardware Group
Team Contract
Task ID: 3
Start Date: 20191016
Finish Date: 20191030
Responsible: Group
Hierarchical LIst
Task ID: 4
Start Date: 20191023
Finish Date: 20191030
Responsible: Group
Engineering specificitation List
Task ID: 5
Start Date: 20191023
Finish Date: 20191030
Responsible: Group
Progect management
Task ID: 6
Start Date: 20191030
Finish Date: 20191105
Responsible: Group
Inventory Lab
Task ID: 1
Start Date: 20191015
Finish Date: 20191022
Responsible: Group
Arduino Lab
Task ID: 2
Start Date: 20191022
Finish Date: 20191029
Responsible: Group